## Hoja1
Sprint Task | March |  | April |  | May |  | June |  | July
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10
T1.1 | Sprint 6: Exam's week
T1.2 | bar: Sprint 3 to Sprint 4
T2.1 | bar: Sprint 2 to Sprint 4
T2.2 | bar: Sprint 3 to Sprint 5
T3.1 | bar: Sprint 7 to Sprint 9
T3.2 | bar: Sprint 9
T4 | bar: Sprint 7 to Sprint 9