## Hoja1
Sprint Task | March |  | April |  | May |  | June
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8
T1.1 | bar: Sprint 1 to Sprint 3
T1.2 | bar: Sprint 3 to Sprint 4
T2.1 | bar: Sprint 2 to Sprint 4
T2.2 | bar: Sprint 3 to Sprint 5
T3.1 | bar: Sprint 5 to Sprint 7
T3.2 | bar: Sprint 5 to Sprint 7
T4 | bar: Sprint 6 to Sprint 8